INVITED IN

Conference-in-Conference Planning Toolkit

A practical planning resource for connecting secondary CTE students with postsecondary experiences

| Host event: |  |
| --- | --- |
| Target audience: |  |
| Lead coordinator: |  |
| Event date: |  |

Use this toolkit as a working document. Adapt, add, and remove items to fit your institution and event.

# 1. Foundation: Define the Model

☐  Identify an existing event that could serve as the host event.

☐  Identify adaptations needed to include the secondary CTE audience.

☐  Define the target audience and determine how you will reach them.

☐  Clarify the purpose: What do you want students, schools, and your institution to gain?

☐  Identify possible partners: faculty, postsecondary students, community/industry partners, student services, admissions, financial aid, or others.

☐  Identify likely constraints early: scale, budget/funding, transportation, staffing, space, timing, partnerships, and administrative support.

## Questions to Shape Decisions

☐  What information do we need from the target audience before designing the experience?

☐  What would influence schools' decision to attend?

☐  What parts of the host event can be shared?

☐  What experiences should be parallel or unique to the secondary audience?

☐  What existing infrastructure can we use rather than recreate?

# 2. Logistics Timeline & Responsibility Sheet

Assign one owner for every task. Add your own due dates and status.

| Phase | Task | Owner | Due | Status/Notes |
| --- | --- | --- | --- | --- |
| EARLY PLANNING | Confirm host event/date/space |  |  |  |
| EARLY PLANNING | Confirm administrative support |  |  |  |
| EARLY PLANNING | Identify target audience/contact list |  |  |  |
| EARLY PLANNING | Survey target audience to inform design |  |  |  |
| EARLY PLANNING | Determine participation model: integrated, parallel, or hybrid |  |  |  |
| EARLY PLANNING | Identify faculty, student, campus, and community partners |  |  |  |
| REGISTRATION | Launch pre-registration with estimated attendance |  |  |  |
| REGISTRATION | Collect administrative/support letter if appropriate |  |  |  |
| REGISTRATION | Set final registration deadline |  |  |  |
| REGISTRATION | Collect student/advisor names |  |  |  |
| REGISTRATION | Collect vehicle type and number for parking planning |  |  |  |
| PROGRAM PREP | Recruit faculty facilitators and confirm center/session needs |  |  |  |
| PROGRAM PREP | Recruit student ambassadors and communicate expectations |  |  |  |
| PROGRAM PREP | Coordinate campus tour route, timing, and tour groups |  |  |  |
| PROGRAM PREP | Create student/ambassador assignments |  |  |  |
| PROGRAM PREP | Create school/group color-coding system |  |  |  |
| PROGRAM PREP | Create name tags with school/group and ambassador information |  |  |  |
| PROGRAM PREP | Determine lunch process, counts, tickets, and location |  |  |  |
| PROGRAM PREP | Determine swag/materials and order/prepare |  |  |  |
| PROGRAM PREP | Prepare agendas, signage, lanyards, packets, and school bundles |  |  |  |
| WEEK OF | Reconfirm faculty, ambassadors, advisors, rooms, and partners |  |  |  |
| WEEK OF | Share final schedules, roles, contacts, parking, and arrival instructions |  |  |  |
| WEEK OF | Prepare contingency plan for cancellations/attendance changes |  |  |  |
| DAY OF | Staff arrival/parking and school-based check-in |  |  |  |
| DAY OF | Place an on-site coordinator at each session/venue |  |  |  |
| DAY OF | Confirm day-of communication method/contact list |  |  |  |
| DAY OF | Position people to support movement and transitions |  |  |  |
| DAY OF | Track last-minute attendance, lunch, material, and schedule changes |  |  |  |
| AFTER | Collect qualitative feedback and participation data |  |  |  |
| AFTER | Document lessons learned and changes for the next event |  |  |  |
| AFTER | Follow up with schools, faculty, ambassadors, and partners |  |  |  |

# 3. Event Preparation Checklist

## Registration & Attendance

☐  Use pre-registration to distinguish interest from likely attendance.

☐  Collect estimated attendance early enough to plan capacity.

☐  Confirm schools have the administrative support/resources needed to attend.

☐  Use final registration to collect student and advisor names.

☐  Build a process for late changes, substitutions, and cancellations.

## Transportation & Parking

☐  Ask each school what it is bringing: cars, vans, minibuses, full-size buses.

☐  Collect the number of each vehicle type.

☐  Confirm where each vehicle type should unload and park.

☐  Send parking/arrival instructions before the event.

☐  Assign a person to parking/arrival who is separate from registration when needed.

## Lunch, Swag & Materials

☐  Determine lunch location, process, counts, tickets/vouchers, and dietary-information process.

☐  Determine what swag/materials participants will receive.

☐  Prepare agendas, name tags, lanyards, bags/packets, and signage.

☐  Bundle high-school materials by school so one advisor can pick up the entire group's materials.

# 4. Program Coordination Checklist

## Faculty

☐  Recruit faculty across relevant disciplines.

☐  Define each faculty member's role and expectations.

☐  Coordinate content, materials, room, timing, and setup for each center/session.

☐  Reconfirm participation close to the event and identify backup options.

## Student Ambassadors

☐  Ask faculty/staff to identify strong postsecondary student leaders.

☐  Recruit ambassadors and clearly communicate their role.

☐  Assign a manageable number of secondary students to each ambassador.

☐  Provide schedule, meeting location, expectations, and contact information.

☐  Reconfirm availability during event week and have a reassignment plan for cancellations.

## Grouping, Tours & Name Tags

☐  Create ambassador/student matches in advance.

☐  Organize tour groups in a way that is easy to recognize and manage.

☐  Use a consistent grouping system across activities.

☐  Include assigned ambassador information on student name tags.

☐  Color-code by school/group when useful for identification and movement.

☐  Build a specific time/location into the schedule for ambassadors and students to find each other.

# 5. Student Ambassador Guidance

Purpose: create an informal peer-to-peer connection that makes the postsecondary experience more personal and accessible.

☐  Know the names/school of the students assigned to you.

☐  Arrive at the designated meeting location early.

☐  Use the provided sign/name-tag information to help students find you.

☐  Introduce yourself and help students get oriented.

☐  Walk with your group to the planned networking/lunch location.

☐  Keep the conversation informal and student-centered.

☐  Share your authentic experience as a postsecondary student; you do not need to 'sell' the institution.

☐  Invite questions about college, the program, campus life, classes, and transition to postsecondary education.

☐  Know who to contact if a student is missing, needs help, or a schedule/logistics issue arises.

☐  Stay with your assigned group for the full ambassador activity unless directed otherwise.

## Suggested Conversation Starters

☐  What are you thinking about doing after high school?

☐  What questions do you have about college?

☐  What surprised you about campus or today's event?

☐  What do you want to know about being a student here?

☐  What made you interested in this career area?

# 6. Communication Plan

Communication is both an advance-planning tool and a day-of contingency system.

| Audience | What they need to know | When | Method | Owner |
| --- | --- | --- | --- | --- |
| School advisors | Registration deadlines; arrival/parking; schedule; supervision; lunch; contact information |  |  |  |
| Faculty | Role; room; timing; materials; participant group; day-of contact |  |  |  |
| Student ambassadors | Role; assigned students; meeting time/location; schedule; day-of contact |  |  |  |
| Campus partners | Role; timing; location; group size; accessibility/logistics |  |  |  |
| Planning team | Changes, cancellations, missing participants, materials, timing, decisions |  |  |  |

## Day-of Communication

☐  Establish one fast way to reach school advisors, faculty, student ambassadors, and coordinators.

☐  Make sure coordinators know who has authority to make schedule/logistics decisions.

☐  Share changes immediately so people have time to pivot.

☐  Keep key items (tickets, materials, contact lists) accessible to the people who may need them.

# 7. Day-of Roles & Venue Coverage

| Location/Function | Coordinator | Primary responsibilities | Backup |
| --- | --- | --- | --- |
| Arrival/Parking |  | Coordinate arrivals, unloading, vehicle placement, late arrivals |  |
| Check-in |  | School-based check-in; distribute prepared school bundles; attendance changes |  |
| Keynote/Shared Session |  | Participant flow, seating, timing, questions |  |
| Hands-on Centers |  | Room/material readiness, timing, transitions, facilitator support |  |
| Campus Tour |  | Group organization, route/timing, transition to next activity |  |
| Lunch/Networking |  | Tickets/vouchers, ambassador meet-up, group issues, transition |  |
| Other session/venue |  | Be physically present; know what should be happening; solve local issues |  |

## Day-of Check

☐  Every session/venue has a named coordinator physically present.

☐  Participants can tell where to go, when to go, and who they are with.

☐  Agendas, name tags, signage, and people reinforce the same organizational system.

☐  Someone other than the lead coordinator can solve routine problems at each location.

# 8. Contingency / Pivot Plan

| If this happens... | Immediate response | Who decides? | Who needs to know? |
| --- | --- | --- | --- |
| Student ambassador cancels |  |  |  |
| Faculty facilitator cancels |  |  |  |
| School arrives late |  |  |  |
| Vehicle parks/unloads in wrong location |  |  |  |
| Student/group assignment changes |  |  |  |
| Lunch ticket/material is missing |  |  |  |
| Room/session timing changes |  |  |  |
| Other: |  |  |  |

# 9. After the Event: Review & Improve

☐  Record actual number of schools and students served.

☐  Collect qualitative feedback from students, advisors, faculty, ambassadors, and partners.

☐  Document what worked and what created friction.

☐  Identify logistics to change next time: parking, lunch, tours, coordination, materials, transitions.

☐  Identify program elements to preserve or strengthen.

☐  Follow up intentionally with participating schools and partners.

☐  Update this toolkit while details are still fresh.

## Year-to-Year Notes

Keep: ___________________________________________________________________________

Change: ___________________________________________________________________________

Add: ___________________________________________________________________________

Stop doing: ___________________________________________________________________________

# 10. Resource Set to Share with the Planning Team

☐  This logistics timeline/responsibility document

☐  Registration/pre-registration forms and support-letter language

☐  Communication templates for school advisors, faculty, and student ambassadors

☐  Student ambassador guidance

☐  Grouping/assignment worksheet

☐  Name-tag/grouping conventions

☐  Parking/arrival instructions

☐  Day-of contact list and venue coordinator assignments

☐  Post-event feedback/reflection questions